## PO OEEM
ANNEX II : PO - FSM (OEEM) | [51 empty] | Ver.4 (Date: March. 4,2015)
Term: 2011 ～ 2015 (5years)
Outputs and Associated Activities |  | Indicators for Outputs | Dept. & Agencies in Charge | Technical Assistance | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/ Eva | JCC
Steering Committee
Evaluation Studies
Output 1-1: The NSWMS in FSM is finalized.
1-1 | Finalize the NSWMS for FSM. | 1-1-1 NSWMS is developed. 1-1-2 Monitoring of the Action Plan is conducte once a year | OEEM | SPREP
1-2 | Conduct the dissemination workshop for other states to explain the SSWMS of Kosrae state. |  | OEEM | SPREP/JICA
1-3 | Facilitate three other states to finalize SSWMS. |  | OEEM
1-4 | Monitore the progress of Action Plan of 4state
1-5 | Modify the NSWMS based on the result of activities in each state. |  | OEEM
1-6 | Draft the next NSWMS for the year 2016-2020. |  | OEEM | (SPREP)
Output 1-2: Information sharing of SWM is enhanced amoung states.
2-1 | Set up an opportunity to share progress and issues of SWM such as in an Environmental conference. | 1-2-1 Set up an meeting for SWM at least once year | OEEM
2-2 | Prepare the document for shaing information of SWM in FSM State | 1-2-2 Document is distributed to 4 states. | OEEM
2-3 | Develop guidline for leachate monitoring | 1-2-3 Guidline is developed and distributed to States | OEEM, Dep. Of Health &Social Affairs

## PO Kosrae
Annex III: Modified PO in Kosrae ver.4 (13-FEB-2015) | [6 empty] | :Done | [11 empty] | :Scheduled but not yet | [13 empty] | ;Scheduled
13/2/2015
Outputs and Associated Activities |  | Indicators for Outputs | Dept. & Agencies in Charge | Technical Assistance | Plan/ Actual | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC
Monitoring Committee
Output 2: State Specific <Kosrae State> Integrated solid waste management is established.
2-1a The SSWMS in Kosrae is finalized. |  | 2-1 SSWMS in Kosrae is developed. 2-2The progress is evaluated accroding to the policy of SSWMS 2-3 Monitoring committee is conducted 3 times per year
2-1-1 | Finalize the SSWMS in Kosrae state. |  | KIRMA |  | Plan | bar: 2011 1 to 2011 5
Actual | bar: 2011 9
2-1-2 | Draft the next SSWMS for the year 2016-2020. |  | KIRMA/DT&I | (SPREP) | Plan | bar: 2015 3 to 2015 12
Actual
2-1b Action plan is developed.
2-1-3 | Prepare the action plan. |  | KIRMA/DT&I | SPREP/JICA | Plan | bar: 2011 9 to 2011 11
Actual | bar: 2011 9 to 2011 11
2-1-4 | Monitor and Review result of the action plan |  | KIRMA |  | Plan | bar: 2014 6; 2015 2; 2015 6; 2015 10
Actual | bar: 2014 7
2-1-5 | After attending training program, Sharing information and experience for other stakeholders in Kosrae |  | KIRMA |  | Plan | bar: 2013 11
Actual | bar: 2013 11
2-2 Collection of General Waste is improved. |  | 2-4 Waste collection system in each municipality is improved.
2-2-1 | Analyze the current collection fee system for all (4) municipalities. |  | KIRMA/DT&I | JICA | Plan | bar: 2012 1 to 2012 3
Actual | bar: 2012 1 to 2012 3; 2012 10
2-2-2 | Identify the issues to improve the current system. |  | KIRMA/DT&I | JICA | Plan
Actual | bar: 2012 2 to 2012 3; 2012 10
2-2-3 | Draft the improvement plan on waste collection |  | Municipalities | KIRMA,(DT&I) | Plan | bar: 2013 11 to 2014 2
Actual
2-3 Waste Disposal is improved. |  | 2-5 Operation and maintenance of landfill is regularly conducted.
2-3-1 | Conduct the baseline study to grasp the current condition of Lelu landfill. |  | DT&I | JICA | Plan | bar: 2011 9 to 2011 11
Actual | bar: 2012 6 to 2012 7
2-3-2 | Develop a improvement plan of Lela landfill. |  | DT&I | JICA | Plan | bar: 2011 11 to 2011 12
Actual | bar: 2012 6 to 2012 7
2-3-3 | Conduct the improvement of Lelu landfill. |  | DT&I |  | Plan | bar: 2011 12 to 2012 2; 2014 3
Actual | bar: 2013 6 to 2014 2
2-3-4 | Conduct the periodical monitoring of the leachate. |  | KIRMA |  | Plan | bar: 2011 12; 2012 6; 2012 12; 2013 6
Actual
2-3-5 | Attending Training program on landfill provided by J-PRISM |  | KIRMA/DT&I | JICA | Plan
Actual | bar: 2012 11; 2013 6
2-4 Awareness Raising is improved |  | 2-46 Educational material for 4R is developed and education for 4Rs is conducted in schools.(2013-: For a pilot school, 2015-: Expand for other less than 4 schools)
2-4-1 | Conduct the dissemination workshop to let the community know about the new recycling /redemption plan. |  | KIRMA | JICA | Plan | bar: 2012 1 to 2012 3
Actual | bar: 2012 1 to 2012 3
2-4-2 | Implement the campaign to introduce the beverage container recycling to schools. |  | KIRMA | JICA | Plan | bar: 2012 1 to 2012 3
Actual | bar: 2012 1 to 2012 3
2-4-3 | Develop educational materials for 4R promotion. |  | KIRMA | Miconesia Eco Inc/JICA | Plan | bar: 2011 12 to 2012 6
Actual | bar: 2011 12 to 2012 11
2-4-4 | Starting school visit and education using educational materials. |  | KIRMA/DOE | Miconesia Eco Inc/JICA | Plan | bar: 2014 6
Actual | bar: 2013 6; 2013 10
2-4-4a | Providing 4R education and teacher training for pilot school . |  | KIRMA/DOE | Miconesia Eco Inc/JICA | Plan | bar: 2013 11 to 2014 8
Actual | bar: 2013 11 to 2014 8
2-4-4b | Expanding effort on 4R education and teachertrining for other schools |  | KIRMA/DOE | Miconesia Eco Inc/JICA | Plan | bar: 2014 9 to 2015 12
Actual | bar: 2014 9 to 2015 2
*
* | E-Waste = Electrical and electronic waste, NSWMS=National Solid Waste Management Strategy, SSWMS=State Solid Waste Management Strategy
KIRMA has been conducting periodical and regular leacheate monitoring
KIRMA has been providing community awareness program.
at Yap
at PNI
W/S
We are here now.
Time&Motion Study
W/S
W/S

## PO Pohnpei
Annex III: Modified PO in Pohpei Ver.4 (27-Feb-2015) | [9 empty] | :Done | [7 empty] | ;Not yet | [9 empty] | :Scheduled
2/27/2015
Outputs and Associated Activities |  | Indicators for Outputs | Dept. & Agencies in Charge | Personnel in charge | Technical Assistance | Plan/ Actual | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/ Eva | JCC
Steering Committee
Evaluation Studies
Output 2: State Specific <Kosrae State> Integrated solid waste management is established.
2-1 Development of the action plan of SSWMS for Kosrae |  | 2-1 The recycle rate for recycables is increased by XX %. (->progress is evaluated accroding to SSWMS or NSWMS) 2-2 Utilization of collected recycables is improved. 2-3 Operation and maintenance of landfill is regularly conducted. 2-4 Educational material for 3R is developed.
2-1-1 | Prepare the action plan. |  | KIRMA/DT&I/OEEM (OEEM should be deleted?) |  | SPREP/JICA
2-1-2 | Implement the action plan. |  | KIRMA/DT&I/OEEM (OEEM should be deleted?)
2-2 Collection of General Waste and Recyclables
2-2-1 | Analyze the current collection fee system for all (4) municipalities. |  | KIRMA/(DT&I) (DT&I should be added?) |  | JICA
2-2-2 | Identify the issues to improve the current system. |  | KIRMA/(DT&I) (DT&I should be added?) |  | JICA
2-2-3 | Draft the plan and carry out necessary activities. |  | KIRMA/(DT&I) (DT&I and municipalities should be added?) |  | JICA
2-2-4 | Document the reference materials of recyclables to be used by other states. |  | OEEM |  | JICA
2-2-5 | Hold the dissemination seminar on collection system of recyclables to other states. |  | OEEM/KIRMA/DT&I |  | JICA
2-3 Waste Disposal
2-3-1 | Conduct the baseline study to grasp the current condition of Lelu landfill. |  | DT&I |  | JICA
2-3-2 | Develop a rehabilitation plan of Lela landfill. |  | DT&I |  | JICA
2-3-3 | Conduct the rehabilitation of Lelu landfill. |  | DT&I
2-3-4 | Conduct the periodical monitoring of the leachate. |  | KIRMA |  | (JICA)
2-4 Awareness Raising
2-4-1 | Conduct the dissemination workshop to let the community know about the new recycling /redemption plan. |  | KIRMA/Recycling Center (Recycling Center should be deleted?) |  | JICA
2-4-2 | Implement the campaign to introduce the beverage container recycling to schools. |  | KIRMA/Recycling Center (Recycling Center should be deleted?) |  | JICA
(2-4-3) | (Develop educational materials for 3R promotion.) |  | KIRMA/DT&I |  | Micronesia Eco Inc/JICA
JCC
Output 3: State Specific <Pohnpei Island> Integrated solid waste management is established.
3-1a The NSWMS and SSWMS in FSM are finalized |  | 3-1-1 SSWMS in Pohnpei is ubmitted to the State for approval. . 3-1-2 Monitoring is conducted 3 times per year by Monitoring committee. 3-1-3 Progress report is prepared by Monitoring committee annually.
3-1-1 | Finalize the SSWMS of Pohnpei. |  | EPA |  |  | Plan
Actual | bar: 2014 2
3-1-2 | Modify the NSWMS and SSWMS based on the result of activities in Pohnpei state. |  | EPA |  |  | Plan
Actual
3-1-3 | Draft the next SSWMS for the year 2016-2020. |  | EPA |  | (SPREP) | Plan
Actual
3-1b Action Plan in Pohnpei is developed.
3-1-4 | Prepare the action plan of SSWMS for Pohnpei. |  | EPA |  | SPREP/JICA | Plan
Actual | bar: 2014 2
3-1-5 | Monitor, Review and Modify action plan. |  | EPA |  |  | Plan | bar: 2014 6; 2014 10; 2015 2; 2015 6; 2015 11
Actual | bar: 2014 6
3-2 Collection of General Waste is improved. |  | 3-2 Plan for improvement of waste collection including fee system, collection method and cooperation with multi municipality, is developed in Sokehs and Kitti, pilot project municipality .
3-2-1 | Conduct the baseline study to grasp the current collection system for general waste. |  | EPA |  | JICA | Plan | bar: 2012 5 to 2012 7
Actual | bar: 2012 5 to 2012 7; 2012 12
3-2-2 | Develop an improvement plan of collection for general waste. |  | EPA |  | JICA | Plan
Actual
3-2-2a | Develop plan for new waste collection system by cooperation among Sokehs and Kitti municipal government. |  | Sokehs, Kitti, EPA |  | JICA | Plan | bar: 2014 3 to 2014 11
Actual
3-3 Final Waste Disposal site is improved. |  | 3-3 Operation under Fukuoka method is introduced for existing dumpsite.
3-3-1 | Review the existing plan for new landfill. |  | EPA, T&I/ Task force |  | JICA | Plan | bar: 2011 6
Actual | bar: 2011 6; 2011 9; 2012 6 to 2012 9
3-3-2 | Raising capability on management of dumpsite/landfill |  | EPA, T&I/ Task force |  | JICA | Plan | bar: 2013 2; 2013 4 to 2013 11
Actual | bar: 2013 2; 2013 6 to 2013 11
3-3-2a | Improvement on management, operation and leachate treatment at existing landfill site. (Documents to be prepared: Report of improvement work and operation manual) |  | T&I, EPA, PWMS |  | JICA | Plan | bar: 2013 12 to 2014 11
Actual | bar: 2013 12 to 2014 11
3-3-2b | Establish plan for landfill in Madolenihmw (Document to be prepared: Plan of landfill in Madolenihmw) |  | Madolenihmw, T&I, EPA |  | JICA | Plan
Actual
3-4 CDL system is improved. |  | 3-4-1 CDL system is operated without unintentional stop. The Recycle Center is operating at least once a month. 3-4-2 The Recycling Law is amended. 3-4-3 Financial system on CDL is improved.
3-4-1 | Monitoring on modification and improvement of the CDL system operation. |  | EPA |  | JICA | Plan | bar: 2014 6; 2014 11; 2015 2; 2015 6; 2015 11
Actual | bar: 2014 6; 2014 12; 2015 2
Output 4: State Specific <Chuuk Island> Disposal site management is improved.
4-1 Development of the action plan of SSWMS for Chuuk |  | 4-1 Operation and maintenance plan is developed reflecting the recommendations
4-1-1 | Prepare the action plan. |  | EPA Chuuk/OEEM |  | SPREP/JICA
4-1-2 | Implement the action plan. |  | EPA Chuuk/OEEM
4-2 Waste Disposal
4-2-1 | Review the improvement plan for existing disposal site. |  | PW /EPA Chuuk |  | JICA
4-2-2 | Draft the recommendation to improve the existing disposal site. |  | PW /EPA Chuuk |  | JICA
4-2-3 | Conduct on-the-job training for operation and maintenance of the disposal site. |  | PW /EPA Chuuk |  | JICA
Output 5: State Specific <Yap Island> Integrated solid waste management is established.
5-1 Development of the action plan of SSWMS for Yap |  | 5-1 Operation and maintenance of landfill is regularly conducted.
5-1-1 | Prepare the action plan. |  | EPA Yap /OEEM |  | SPREP/JICA
5-1-2 | Implement the action plan. |  | EPA Yap /OEEM
5-2 Waste Disposal
5-2-1 | Review the current plan of construction of landfill by applying Fukuoka method. |  | PW &I /EPA Yap |  | JICA
5-2-2 | Train C/Ps on operation and maintenance of landfill by applying Fukuoka method. |  | PW &I /EPA Yap |  | JICA
5-2-3 | Operate and maintain the landfill. |  | PW &I
5-3 Awareness Raising
5-3-1 | Promote the understanding of the solid waste management to communities and schools. |  | PW &I /EPA Yap |  | JICA
5-3-2 | Implement the segregation of general waste at household level for the main Island. |  | PW &I /EPA Yap
5-3-3 | Improve awareness of recycling activities and other waste minimization activities including composting, etc. |  | PW &I /EPA Yap |  | JICA
* | FSM=Federal States of Micronesia, OEEM= Office of Environment and Emergency Management, EPA=Environmental Protection Agency, T&I= Transportation & Infrastructure, PWMS=Pohnpei Waste Management Seavice
* | E-Waste = Electrical and electronic waste, NSWMS=National Solid Waste Management Strategy, SSWMS=State Solid Waste Management Strategy
We are here now.
Yap
Training
Pohnpei
Training
Time &
Motion study
Planed in 2016 & 2018.

## PO Chuuk
ANNEX III-2 : PO - FSM (Chuuk)
Term: 2011 ～ 2015 (5years) | [53 empty] | Version.4（ Feb. 2015）
Outputs and Associated Activities |  | Indicators for Outputs | Dept. & Agencies in Charge | Responsible Person | Technical advice &guidance | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/ Eva | JCC
Steering Committee
Evaluation Studies
Output 4-1: Capacity to prepare the State Solid Waste Management Strategy of Chuuk and Action plan is developed.
1-2 | Hold in-country trainings for general SWM and workshop for making detail plan of operation in Chuuk State | 1-1 NSWMS and SSWMS for all four states are developed. | OEEM /KIRMA, EPAs for Pohnpei, Chuuk and Yap | Jack Sham | JICA /SPREP | bar: 2011 1 to 2011 5
4-1-1 | Hold in-country trainings for general SWM and workshop for making detail plan of operation in Chuuk State | 4-1-1 Chuuk SSWMS is submitted to the State for approval 4-1-2 Monitoring on the progress of Action Plan is conducted annually | EPA/ PW | Jack Sham | JICA /SPREP | bar: 2011 9 to 2011 11
4-1-2 | Conduct the survey to collect the data and information of current SWM situation in Chuuk state. |  | EPA/ PW | Jack Sham | JICA | bar: 2011 3 to 2011 4; 2012 2; 2012 4; 2013 3; 2015 3 to 2015 5
4-1-3 | Facilitate the Kosrae state to finalize SSWMS. |  | OEEM |  | JICA | bar: 2011 7 to 2011 9
4-1-4 | Finalize the SSWMS in Kosrae state. |  | KIRMA |  | JICA | bar: 2011 9
4-1-5 | Conduct the dissemination workshop for other states to explain the SSWMS of Kosrae state. |  | OEEM / KIRMA |  | JICA | bar: 2011 10
4-1-6 | Facilitate three other states to finalize SSWMS. |  | OEEM |  | JICA | bar: 2011 10 to 2011 11; 2012 1 to 2012 3
4-1-3 | Prepare the SSWMS and Action plan. |  | EPA/ PW | Ismael Mikel/ Joanes Risin | SPREP/ JICA | bar: 2012 3 to 2012 5
4-1-4 | Finalize the SSWMS of Chuuk State. |  | EPA/ PW | Ismael Mikel | bar: 2012 10 to 2012 11
4-1-10 | Participate the training /workshop for Micronesian area conducted by Palau. |  |  | Ismael Mikel | Palau/SPREP/ JICA | bar: 2014 6; 2015 4
4-1-5 | Monitor the progress of the Action Plan and Modify the SSWMS or Action Plan if necessary |  | EPA/ PW | Ismael Mikel/ Joanes Risin | bar: 2014 1 to 2014 2; 2015 1 to 2015 2
4-1-6 | Draft the next SSWMS for the year 2016-2020. |  | EPA/ PW | Jack Sham | (SPREP) | bar: 2015 3 to 2015 8
Output 2: State Specific <Kosrae State> Integrated solid waste management is established.
2-1 Development of the action plan of SSWMS for Kosrae |  | 2-1 The recycle rate for recyclables is increased by XX %. 2-2 Utilization of collected recyclables is improved. 2-3 Operation and maintenance of landfill is regularly conducted.
2-1-1 | Prepare the action plan. |  | KIRMA/DT&I/OEEM |  | SPREP/JICA | bar: 2011 9 to 2011 11
2-1-2 | Implement the action plan. |  | KIRMA/DT&I/OEEM | bar: 2012 1 to 2015 12
2-2 Collection of General Waste and Recyclables
2-2-1 | Analyze the current collection fee system for all (4) municipalities. |  | KIRMA |  | JICA | bar: 2012 1 to 2012 3
2-2-2 | Identify the issues to improve the current system. |  | KIRMA |  | JICA | bar: 2012 2 to 2012 6
2-2-3 | Draft the plan and carry out necessary activities. |  | KIRMA |  | JICA | bar: 2012 7 to 2015 12
2-2-4 | Document the reference materials of recyclables to be used by other states. |  | OEEM |  | JICA | bar: 2013 1 to 2013 4
2-2-5 | Hold the dissemination seminar on collection system of recyclables to other states. |  | OEEM/KIRMA/DT&I |  | JICA | bar: 2013 10; 2015 5
2-3 Waste Disposal
2-3-1 | Conduct the baseline study to grasp the current condition of Lelu landfill. |  | DT&I |  | JICA | bar: 2011 9 to 2011 11
2-3-2 | Develop a rehabilitation plan of Lela landfill. |  | DT&I |  | JICA | bar: 2011 11 to 2011 12
2-3-3 | Conduct the rehabilitation of Lelu landfill. |  | DT&I | bar: 2011 12 to 2012 2
2-3-4 | Conduct the periodical monitoring of the leachate. |  | KIRMA |  | (JICA) | bar: 2011 12; 2012 6; 2012 12; 2013 6; 2013 12; 2014 6; 2014 12; 2015 6; 2015 12
2-4 Awareness Raising
2-4-1 | Conduct the dissemination workshop to let the community know about the new recycling /redemption plan. |  | KIRMA/Recycling Center |  | JICA | bar: 2012 1 to 2012 3; 2012 8; 2013 2; 2013 8; 2014 2; 2014 8; 2015 2; 2015 8
2-4-2 | Implement the campaign to introduce the beverage container recycling to schools. |  | KIRMA/Recycling Center |  | JICA | bar: 2012 1 to 2012 3
Output 3: State Specific <Pohnpei Island> Integrated solid waste management is established.
3-1 Development of the action plan of SSWMS for Pohnpei |  | 3-1 Collection area of general waste is increased.
3-1-1 | Prepare the action plan of SSWMS for Pohnpei. |  | EPA Pohnpei/OEEM |  | SPREP/JICA | bar: 2012 7 to 2012 9
3-1-2 | Implement the action plan. |  | EPA Pohnpei/OEEM | bar: 2012 10 to 2015 12
3-2 Collection of General Waste
3-2-1 | Conduct the baseline study to grasp the current collection system for general waste. |  | EPA Pohnpei |  | JICA | bar: 2012 10 to 2012 12
3-2-2 | Develop an expansion plan of collection for general waste. |  | EPA Pohnpei |  | JICA | bar: 2013 1 to 2013 3
3-2-3 | Prepare the necessary conditions, such as the budget allocation, legal framework, machinery and equipment, etc. in order to implement the expansion plan. |  | EPA Pohnpei | bar: 2013 4 to 2013 12
3-2-4 | Implement the expansion plan to Pohnpei main Island. |  | EPA Pohnpei | bar: 2014 1 to 2015 12
3-3 Waste Disposal
3-3-1 | Review the existing plan for new landfill. |  | T&I |  | JICA | bar: 2011 6
3-3-2 | Train C/Ps on operation and maintenance for the new landfill by applying Fukuoka method. |  | T&I |  | JICA | bar: 2013 1
4-2: Capacity to improve and manage the final disposal site is enhanced
4-2-1 | Review the improvement plan for existing disposal site and recommendation to improve the site is prepared. | 4-2-1 Boundary of the existing dumpsite is identified and separated from other area. 4-2-2 Operation of compacting waste is conducted at least once a week. 4-2-3 Operation is recorded and submitted to PW and EPA. | PW /EPA Chuuk | Jack Sham/ John Newo | JICA | bar: 2011 3 to 2011 12
4-2-2 | Finalize the improvement plan for existing disposal site. |  | PW /EPA Chuuk | Jack Sham/ John Newo | JICA | bar: 2012 1 to 2012 2
4-2-3 | Implement the improvement plan. |  | PW /EPA Chuuk | Jack Sham/ John Newo | JICA | bar: 2013 3 to 2013 8
4-2-4 | Conduct on-the-job training for operation and maintenance of the disposal site. |  | PW /EPA Chuuk | Jack Sham/ John Newo | JICA | bar: 2013 2; 2014 7 to 2014 8
4-3: Capacity to improve the collection of general waste is enhanced.
4-3-1' | Conduct a Pilot Project of waste collection | 4-3-1 Monthly collection record is submitted to PW and EPA. 4-3-2 More than 5 villages receive regular collection service. 4-3-3 More than 10 workshops are conducted to improve the waste dischrge of the people. | PW /EPA Chuuk | Joanes | bar: 2012 6 to 2012 9
4-3-2' | Conduct Time and Motion Study to find issues of collection system |  | PW /EPA Chuuk | Joanes | JICA | bar: 2012 10 to 2012 11
4-3-3' | Develop a collection plan based on the study conducted. |  | PW /EPA Chuuk | Joanes | JICA | bar: 2012 11
4-3-4' | Revise /develop a collection route and frequency when collection area is expanded. |  | PW /EPA Chuuk | Joanes | bar: 2013 1
4-3-5' | Plan awareness activity to commercial sectors and public to improve collection service. |  | EPA/PW | Jack | bar: 2013 5; 2014 5
4-3-6' | Conduct awareness activities |  | EPA/PW | Jack | bar: 2014 6 to 2015 12
* | FSM=Federal States of Micronesia, OEEM= Office of Environment and Emergency Management, KIRMA=Kosrae Island Resource Management Authority, DT&I= Department of Transportation and Infrastructure, EPA=Environmental Protection Agency, T&I= Transportation & Infrastructure, PW= Public Works, PW&T = Public Works & Transportation, R&D=Department of Resources & Development
* | E-Waste = Electrical and electronic waste, NSWMS=National Solid Waste Management Strategy, SSWMS=State Solid Waste Management Strategy

## PO Yap
ANNEX II : PO - FSM (Yap)
Term: 2011 ～ 2015 (5years) | [53 empty] | Version. 4 (Feb. 2015)
Outputs and Associated Activities |  | Indicators for Outputs | Dept. & Agencies in Charge | Person in Charge | Technical advice & guidance | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/ Eva | JCC
Steering Committee
Evaluation Studies
Output 5-1: Capacity to prepare the State Solid Waste Management Strategy of Yap State and Action Plan is developed.
5-1-1 | Hold in-country trainings for general SWM and workshop for making detail plan of operation in Yap state. | 5-1-1 Yap SSWMS is submitted to the State for approval 5-1-2 Action Plan is distributed to the stakeholders 5-1-3 Monitoring on the progress of Action Plan is conducted annually | EPA/ PW&T | Christina | JICA/ SPREP | bar: 2011 11
1-2 | Finalize the NSWMS for FSM. |  | OEEM |  | SPREP | bar: 2011 1 to 2011 5
5-1-2 | Conduct the survey to collect the data and information of current SWM situation in Yap state. |  | EPA/ PW&T | Christina/ Manuel | JICA | bar: 2011 3; 2012 5; 2013 3; 2015 3 to 2015 5
1-4 | Facilitate the Kosrae state to finalize SSWMS. |  | OEEM |  | (SPREP) | bar: 2011 7 to 2011 9
1-5 | Finalize the SSWMS in Kosrae state. |  | KIRMA | bar: 2011 9
1-6 | Conduct the dissemination workshop for other states to explain the SSWMS of Kosrae state. |  | OEEM / KIRMA |  | SPREP/JICA | bar: 2011 10
1-7 | Facilitate three other states to finalize SSWMS. |  | OEEM | bar: 2011 10 to 2012 3
5-1-3 | Prepare the SSWMS and Action plan. |  | EPA Yap /OEEM | Christina | SPREP/ JICA | bar: 2012 4 to 2012 7
5-1-4 | Finalize the SSWMS of Yap state. |  | EPA/ PW&T | Christina | bar: 2013 12 to 2014 1
1-9 | Participate the training /workshop for Micronesian area conducted by Palau. |  |  |  | Palau/SPREP/ JICA | bar: 2014 6; 2015 4
5-1-5 | Monitor the progress of the Action Plan |  | EPA/ PW&T | Christina/ Manuel | bar: 2014 2 to 2014 3; 2015 1 to 2015 2
5-1-6 | Modify the SSWMS and its Action Plan based on the result of activities if necessary. |  | EPA/ PW&T | Christina | bar: 2014 3
5-1-7 | Draft the next SSWMS for the year 2016-2020. |  | EPA/ PW&T | Christina | (SPREP)
Output 2: State Specific <Kosrae State> Integrated solid waste management is established.
2-1 Development of the action plan of SSWMS for Kosrae |  | 2-1 The recycle rate for recyclables is increased by XX %. 2-2 Utilization of collected recyclables is improved. 2-3 Operation and maintenance of landfill is regularly conducted.
2-1-1 | Prepare the action plan. |  | KIRMA/DT&I/OEEM |  | SPREP/JICA | bar: 2011 9 to 2011 11
2-1-2 | Implement the action plan. |  | KIRMA/DT&I/OEEM | bar: 2012 1 to 2015 12
2-2 Collection of General Waste and Recyclables
2-2-1 | Analyze the current collection fee system for all (4) municipalities. |  | KIRMA |  | JICA | bar: 2012 1 to 2012 3
2-2-2 | Identify the issues to improve the current system. |  | KIRMA |  | JICA | bar: 2012 2 to 2012 6
2-2-3 | Draft the plan and carry out necessary activities. |  | KIRMA |  | JICA | bar: 2012 7 to 2015 12
2-2-4 | Document the reference materials of recyclables to be used by other states. |  | OEEM |  | JICA | bar: 2013 1 to 2013 4
2-2-5 | Hold the dissemination seminar on collection system of recyclables to other states. |  | OEEM/KIRMA/DT&I |  | JICA | bar: 2013 10; 2015 5
2-3 Waste Disposal
2-3-1 | Conduct the baseline study to grasp the current condition of Lelu landfill. |  | DT&I |  | JICA | bar: 2011 9 to 2011 11
2-3-2 | Develop a rehabilitation plan of Lela landfill. |  | DT&I |  | JICA | bar: 2011 11 to 2011 12
2-3-3 | Conduct the rehabilitation of Lelu landfill. |  | DT&I | bar: 2011 12 to 2012 2
2-3-4 | Conduct the periodical monitoring of the leachate. |  | KIRMA |  | (JICA) | bar: 2011 12; 2012 6; 2012 12; 2013 6; 2013 12; 2014 6; 2014 12; 2015 6; 2015 12
2-4 Awareness Raising
2-4-1 | Conduct the dissemination workshop to let the community know about the new recycling /redemption plan. |  | KIRMA/Recycling Center |  | JICA | bar: 2012 1 to 2012 3; 2012 8; 2013 2; 2013 8; 2014 2; 2014 8; 2015 2; 2015 8
2-4-2 | Implement the campaign to introduce the beverage container recycling to schools. |  | KIRMA/Recycling Center |  | JICA | bar: 2012 1 to 2012 3
Output 3: State Specific <Pohnpei Island> Integrated solid waste management is established.
3-1 Development of the action plan of SSWMS for Pohnpei |  | 3-1 Collection area of general waste is increased.
3-1-1 | Prepare the action plan of SSWMS for Pohnpei. |  | EPA Pohnpei/OEEM |  | SPREP/JICA | bar: 2012 7 to 2012 9
3-1-2 | Implement the action plan. |  | EPA Pohnpei/OEEM | bar: 2012 10 to 2015 12
3-2 Collection of General Waste
3-2-1 | Conduct the baseline study to grasp the current collection system for general waste. |  | EPA Pohnpei |  | JICA | bar: 2012 10 to 2012 12
3-2-2 | Develop an expansion plan of collection for general waste. |  | EPA Pohnpei |  | JICA | bar: 2013 1 to 2013 3
3-2-3 | Prepare the necessary conditions, such as the budget allocation, legal framework, machinery and equipment, etc. in order to implement the expansion plan. |  | EPA Pohnpei | bar: 2013 4 to 2013 12
3-2-4 | Implement the expansion plan to Pohnpei main Island. |  | EPA Pohnpei | bar: 2014 1 to 2015 12
3-3 Waste Disposal
3-3-1 | Review the existing plan for new landfill. |  | T&I |  | JICA | bar: 2011 6
3-3-2 | Train C/Ps on operation and maintenance for the new landfill by applying Fukuoka method. |  | T&I |  | JICA | bar: 2013 1
Output 4: State Specific <Chuuk Island> Disposal site management is improved.
4-1 Development of the action plan of SSWMS for Chuuk |  | 4-1 Operation and maintenance plan is developed reflecting the recommendations
4-1-1 | Prepare the action plan. |  | EPA Chuuk/OEEM |  | SPREP/JICA | bar: 2012 7 to 2012 9
4-1-2 | Implement the action plan. |  | EPA Chuuk/OEEM | bar: 2012 10 to 2015 12
4-2 Waste Disposal
4-2-1 | Review the improvement plan for existing disposal site. |  | PW /EPA Chuuk |  | JICA | bar: 2011 6
4-2-2 | Draft the recommendation to improve the existing disposal site. |  | PW /EPA Chuuk |  | JICA | bar: 2011 6
4-2-3 | Conduct on-the-job training for operation and maintenance of the disposal site. |  | PW /EPA Chuuk |  | JICA | bar: 2012 10; 2013 7
5-2: Capacity to improve and manage the final disposal site is enhanced.
5-2-1 | Review the current plan of construction of landfill by applying Fukuoka method. | 5-2-1 New landfill design is developed. 5-2-2 More than 10 counterparts get certificate in the training of operation and maintenance of landfill 5-2-3 The upgrade of the existing dumpsite to semi-aerobic is completed . 5-2-4 Operation of new landfill is monitored by EPA monthly according to the new landfill management plan | PW &T/EPA Yap | Vincent/ Christina | JICA | bar: 2011 4 to 2011 9
5-2-2 | Collect data of incoming waste at dumpsite |  | PW&T/ EPA | Jesse
5-2-3 | Finalize the revised plan of construction of landfill |  | PW &T/EPA Yap | Vincent/ Christina | bar: 2011 10 to 2012 1
5-2-4 | Train C/Ps on operation and maintenance of landfill by applying Fukuoka method. |  | PW &T /EPA Yap | Vincent | JICA | bar: 2013 2
5-2-5 | Operate and maintain the new landfill. |  | PW &T | Jesse | bar: 2015 3 to 2015 12
5-2-6 | Plan to rehabilitate the existing dumpsite |  | PW &T | Jesse | JICA | bar: 2014 11
5-2-7 | Rehabilitate an existing dumpsite |  | PW &T | Jesse | bar: 2015 2 to 2015 3
5-3: Capacity to conduct awareness activities for SWM is raised.
5-3-1 | Prepare awareness program/materials (1) | 5-3-1 More than 10 workshops are conducted at schools and communities using the awareness materials developed 5-3-2 Awareness of SWM through a questionnaire result is raised by 25% | EPA Yap | Christina | JICA | bar: 2012 11 to 2013 2
5-3-2 | Conduct schools/ community visits |  | EPA Yap | Christina | bar: 2013 3 to 2014 4
5-3-3 | Evaluate the program |  | EPA Yap | Christina | JICA | bar: 2013 6
5-3-4 | Prepare awareness program/materials (2) |  | EPA Yap | Christina | JICA | bar: 2014 5 to 2014 6
5-3-5 | Conduct awareness program (2) |  | EPA Yap | Christina | bar: 2014 7 to 2015 12
5-3-6 | Evaluate the program |  | EPA Yap | Christina | JICA | bar: 2015 11 to 2015 12
* | FSM=Federal States of Micronesia, OEEM= Office of Environment and Emergency Management, KIRMA=Kosrae Island Resource Management Authority, DT&I= Department of Transportation and Infrastructure, EPA=Environmental Protection Agency, T&I= Transportation & Infrastructure, PW= Public Works, PW&T = Public Works &Transportation, R&D=Department of Resources & Development
* | E-Waste = Electrical and electronic waste, NSWMS=National Solid Waste Management Strategy, SSWMS=State Solid Waste Management Strategy